## 25-11 MON
| Task Hours Assigned (min) | 480 | Task Hours Completed (Min) | 510
Sr. No |  | Time Start | Time End | Total time spent(min) | Domain | Task Details | Task status | Test URL
1 | mit | 10:00 | 12:00 | 120 | HRMS | Setting up multiple check-in and check-out functionality on the HRMS Dashboard | completed | local
2 | mit | 12:00 | 1:30 | 90 | HRMS | Refactoring the Break-in and Break-out APIs for both on site and field employees | completed | local
3 | mit | 2:00 | 6:30 | 270 | Marwiz | Creating new module for creating personalized media queue to make multiple small queues of media with stakeholder and max time | completed | local
4 | mit | 6:30 | 7:00 | 30 | Topland | small call on new topland changes and feature discussen | completed | local
|  |  | HRMS | 210
|  |  | Marwiz | 270
|  |  | Topland | 30

## 26-11 TUE
| Task Hours Assigned (min) | 480 | Task Hours Completed (Min) | 480
Sr. No |  | Time Start | Time End | Total time spent(min) | Domain | Task Details | Task status | Test URL
1 | self | 9:15 | 10:00 | 45 | Topland | clearing old node version error and Setting up new Admin panel on github with latest pushed code | completed | local
2 | self | 10:00 | 10:30 | 30 | Topland | Meeting with the cliend reguarging changes and new functionalities | completed | local
3 | self | 10:30 | 1:00 | 150 | Topland | Creating new Date wise Appointment master in place of week wise to create slots manually | completed | local
4 | self | 2:15 | 4:30 | 135 | Topland | Changes in Promocode master to store meximum number of redemption and also multiply the discount with the number of slots selected | completed | local
5 | self | 4:30 | 6:30 | 120 | Topland | display the appointments date wise rather than week wise in all 4 category booking pages as well as admin panel blocking page | completed | local
|  |  | Topland | 480

## 27-11 WED
| Task Hours Assigned (min) | 480 | Task Hours Completed (Min) | 485
Sr. No |  | Time Start | Time End | Total time spent(min) | Domain | Task Details | Task status | Test URL
1 | self | 9:10 | 11:30 | 140 | Topland | Adding validations for maximum redemptions as well as personalised Promocodes for 4 categories | completed | https://admintopland.barodaweb.org/
2 | self | 11:30 | 1:30 | 120 | WeHear | meeting with kanishka sir and team reguarging new changes old flow changes and defining the timelines and document update for the same | completed | local
3 | self | 3:00 | 4:30 | 90 | Topland | Dispaly the remaining quantity of delegates on admin side as well as user side date wise | completed | https://admintopland.barodaweb.org/
5 | self | 4:30 | 6:45 | 135 | HRMS | Solving firebase , PMS data fetching and duplicate models error in HRMS server | completed | https://hrms.bizgrowthsolution.com/
|  |  | Topland | 230
|  |  | HRMS | 135
|  |  | WeHear | 120

## 28-11 THU
| Task Hours Assigned (min) | 480 | Task Hours Completed (Min) | 570
Sr. No |  | Time Start | Time End | Total time spent(min) | Domain | Task Details | Task status | Test URL
1 | self | 9:00 | 11:30 | 150 | Topland | Complete/Partial Appointment Blocking category,day,date and slot wise | completed | local
2 | self | 11:30 | 1:15 | 105 | Topland | User Side Calender date blocking for empty dates with no slot, Creating new APIs to Give all Types of counts of slot booking weekly monthly and day-wise | completed | local
3 | self | 2:00 | 3:15 | 75 | HMS | removing middlewaes and adding static routes for temparory use and solving the vesion error in task and leave forms | completed | local
4 | self | 3:15 | 6:45 | 210 | Topland | Separate celander view for Showing monthly updates of booking with fully booked partially booked and empty slots with colour schema and number of blocked, booked and remianing slots | in Process | local
5 | self | 6:45 | 7:15 | 30 | Topland | Uploading both Admin and User panel on live server | completed | local
|  |  | Topland | 495
|  |  | HRMS | 75

## 29-11 FRI
| Task Hours Assigned (min) | 480 | Task Hours Completed (Min) | 505
Sr. No |  | Time Start | Time End | Total time spent(min) | Domain | Task Details | Task status | Test URL
1 | self | 9:15 | 12:00 | 165 | Topland | Room Master Dynamic category and Max Booking API and intigration | completed | local
2 | self | 12:00 | 1:00 | 60 | Topland | Admin Panel Nav-Bar changes according to new menu strucutre and routes and | completed | local
3 | self | 2:00 | 4:25 | 145 | Topland | Booked Appointment Status Update marking that attended , not attended or not paid also allow Admin To Delete cannceled appointment | completed | local
4 | self | 4:25 | 6:30 | 135 | Topland | Payment Gateway Callback URL changes and status fetching paid-unpaid and outlook mailing documentation | completed | local
|  |  | Topland | 505

## 30-11 SAT
| Task Hours Assigned (min) | 480 | Task Hours Completed (Min) | 315
Sr. No |  | Time Start | Time End | Total time spent(min) | Domain | Task Details | Task status | Test URL
1 | self | 9:30 | 1:00 | 210 | Topland | Completed the Dashboard with Date,month and category wise Gapths and Cards | completed | local
2 | self | 2:00 | 3:45 | 105 | Topland | Completed Remaining changes, errors and live the code the final version of the code on live sever | completed | local
|  |  | Topland | 315